# Predicting OCD Severity: Impact of demographic and clinical features

# project charter

# TABLE OF CONTENTS

1	Introduction	3

1.1	Purpose of Project Charter	3

2	project And Product Overview	3

3	Justification	3

3.1	Business Need	3

3.2	Public Health and Business Impact	3

3.3	Strategic Alignment	4

4	Scope	6

4.1	Objectives	6

4.2	High-Level Requirements	7

4.3	Major Deliverables	7

4.4	Boundaries	8

5	Duration	8

5.1	Timeline	8

5.2	Executive Milestones	9

6	budget Estimate	10

6.1	Funding Source	10

6.2	Estimate	10

7	High-Level Alternatives Analysis	10

8	Assumptions, Constraints And Risks	11

8.1	Assumptions	11

8.2	Constraints	11

8.3	Risks	12

9	Project Organization	12

9.1	Roles and Responsibilities	12

9.2	Stakeholders (Internal and External)	14

9.3	Development approach	15

10	project Charter approval	15

APPENDIX A: DOCUMENTATION	16

APPENDIX B: Refernces	17

# Introduction

## Purpose of Project Charter

The purpose of the project charter for the project "Predicting OCD Severity: Impact of Demographic and Clinical Features" is to document and compile the information necessary for decision-makers to approve the project for funding and resource allocation. The project charter will outline the project's needs, scope, justification, and resource commitments, and provide the project's manager and business lead with the necessary information to decide whether to proceed with the project.

The project aims to develop a model that predicts the severity of obsessive-compulsive disorder (OCD) based on demographic and clinical factors in 1,500 patients. This will help healthcare professionals and researchers identify high-risk patients and enable more individualized treatment strategies. For this pilot phase, we will use a synthetic dataset provided by stakeholders. This approach allows us to test and refine the model while ensuring data security and compliance with privacy regulations before applying it to real patient data.

The intended audience for this project charter includes stakeholders such as project management, data scientists, healthcare professionals, governmental health agencies, and technology partners.

# project And Product Overview

This project aims to develop a model to predict the severity of OCD based on demographic and clinical data from 1500 patients diagnosed with OCD. The project will last for an estimated period of 8 weeks and is estimated to have a budget of approximately SEK 600.000. The dashboard that will be created as part of this project is intended for use by healthcare professionals and researchers to analyze and visualize factors that influence OCD severity. The dashboard enables users to identify patterns and relationships between various patient characteristics and OCD severity, enabling more personalized care. The dashboard will also show if obsession or compulsion is the dominant feature.

# Justification

## Business Need

OCD is a chronic disease that worsens the mental conditions of patients.  Delayed or inaccurate treatment can exacerbate symptoms worsening daily lives [1]. This could lead to more hospital costs and financial burdens to patients and the government. This disease can also affect productivity and the economy by reducing the number of people available for work. Thus, early detection of disease severity with the help of a prediction model using a machine learning algorithm is beneficial to avoid such negative impacts, saving financial and human resources.

## Public Health and Business Impact

OCD is a chronic mental disease that is seriously disrupting the daily activities of patients. It affects 2-3% of the global population [1]. Accurate prediction of its severity from the patient conditions using data science could allow more timely and precise medical intervention. This could reduce the patient’s symptoms and cure the disease, improving the quality of life, and productivity, and providing a positive effect on the health status of the community.

With the help of a predictive model of OCD severity scores, data-driven decisions can be made by mental health professionals, leading to timely and accurate medical treatment of OCD patients. This can optimize resource allocation, reduce healthcare costs and financial burden, and increase the efficiency of patient management, improving clinical outcomes.

## Strategic Alignment

| Goal | Project Response Rank | Comments |
| --- | --- | --- |
| Scale: H – High, M- Medium, L – Low, N/A – Not Applicable |  |  |
| NC / Division / Branch Strategic Goals: |  |  |
| The National Center for Chronic Disease Prevention and Health Promotion (NCCDPHP) aims to enhance the health and wellness of people from the US by preventing and managing chronic disease. It has priorities such as: “Using data to address health equity and social determinants of health challenges” [2] | H | It intends to use data and technology to solve health problems to achieve the goals of managing chronic diseases like OCD. Thus, it is highly relevant to our project using data for better treatment of OCD. |
| “Modernizing legacy information technology and surveillance systems” [2] | M | It aims to improve IT and disease surveillance to acquire better data for deployment. |
| CDC Strategic Goals: |  |  |
| “Advancing Science and Health Equity” [3] | H | This strategic plan emphasizes developing world-class data analytics and transforming data into public health action, which is highly relevant to our project. |
| Department of Health and Human Services (DHHS) Strategic Goals: |  |  |
| Goal 3: “Strengthen Social Well-being, Equity, and Economic Resilience” [4] | H | This aims to improve the well-being and economic success of families so it is highly relevant to our project for addressing a mental health issue, OCD. |
| Goal 4: “Restore Trust and Accelerate Advancements in Science and Research for All” [5] | H | It supports advancement in scientific research, aligning with our data science project. |
| DHHS IT Goals: |  |  |
| Goal 3: “Build a Secure, Data-Driven Ecosystem to Accelerate Research and Innovation” [6] | H | It has strategic plans to leverage the Health IT and data ecosystem to promote health and wellness. Thus, they are highly related to our project. |
| Goal 2: “Enhance the Delivery and Experience of Care” [6] | M | It aims to improve the quality and efficiency of healthcare through advanced IT solutions. |
| President’s Management Agenda (PMA) Strategic Goals: |  |  |
| Priority 2: “Delivering Excellent, Equitable, and Secure Federal Services and Customer Experience” [7] | M | This goal aims to improve federal services, which also include healthcare, ensuring equitable and effective services. |
| Priority 3: “Managing the Business of Government” [8] | L | It includes the use of data and technology to improve business and financial management. |
| Karolinska Institutet's strategy and core values: |  |  |
| Overarching Objectives 2: “A deep global, national, and local commitment to human health shall characterize our education and research.” [9] | H | Our project focuses on descriptive, diagnostic, and predictive analytics of mental health data intending to improve OCD treatment outcomes. So, it is highly related to KI strategies. |
| Overarching Objectives 3: “A richness of perspectives shall define our education and research. Education and research shall be tightly coupled and synergies explored.” [9] | M | Our project aims to search for the best predictive model for OCD severity, it promotes education and research in the healthcare area. |
| Folkhalsomyndigheten (Public Health Agency) Mission: |  |  |
| Its overall goal is to focus on equal health, creating social conditions for good, equal health in the entire population, and reduce the health inequalities in a generation [10] | H | As our project intends to support decision-making in OCD treatment to all kinds of patients, using data science, it could be highly relevant to the goal of public health agency. |

# Scope

## Objectives

The objectives of the Predicting OCD Severity: Impact of Demographic and Clinical Features are as follows:

- Develop a predictive model that can assist healthcare professionals in identifying whether Obsessions or Compulsions are likely to be the dominant feature in patients with OCD, based on easily obtainable patient information

- Develop a model that predicts the severity of OCD symptoms (as measured by the Y-BOCS score) based on demographic and clinical features, which can be used for risk stratification

- Identify which features have the most significant influence on whether obsessions or compulsions are dominant and on the severity of OCD symptoms

- Provide a data-driven approach to OCD treatment planning and allocation of mental health resources  by allowing for more precise therapeutic approaches and personalized care plans

- Reveal patterns and correlations that deepen the understanding of how OCD symptoms manifest across different populations

## High-Level Requirements

The following table presents the requirements that the project’s product, service or result must meet in order for the project objectives to be satisfied.

| Req. # | Requirement Description |
| --- | --- |
| 1 | The system should accept data entries for relevant attributes based on the limitations that are agreed upon and set (For eg, age ranges from 21 to 100). |
| 2 | The model must provide transparent reasoning behind predictions, including which features (e.g., age, family history) contributed most to the prediction. |
| 3 | The system should create an alert if the total Y BOCS score is predicted to be above 30 so that these patients can be prioritized. |
| 4 | The system must comply with healthcare regulations, such as GDPR, to ensure data privacy and security. |
| 5 | The solution should integrate with existing Electronic Health Record (EHR) systems |

## Major Deliverables

The following table presents the major deliverables that the project’s product, service or result must meet in order for the project objectives to be satisfied.

| Major Deliverable | Deliverable Description |
| --- | --- |
| Structured Dataset | A comprehensive dataset containing relevant features such as age, gender, family history of OCD, duration of symptoms, obsession type, compulsion type, and Y-BOCS scores for obsessions and compulsions. The dataset should be handled for missing values, data should be normalized and categorical variables should be encoded. Anonymization should be done to comply with data privacy regulations. |
| Exploratory Data Analysis | Initial data analysis for visualization, identification of outliers, finding correlations between features and target variables and identification of any potential bias in the dataset. |
| Trained classification models with performance evaluation | A trained and validated classification model to predict whether obsessions or compulsions are the dominant feature based on input data. The model should achieve a predefined level of accuracy, precision, recall, and F1-score, with explainable outputs. |
| Trained regression models with performance evaluation | A trained and validated regression model to predict the severity of OCD symptoms based on Y-BOCS scores for obsessions and compulsions. The model must be evaluated using Mean Squared Error (MSE). |
| Model Validation | Validation of the model’s performance by testing on unseen data. |
| Testing and Demonstration | Pilot testing, user manuals, technical documentation |
| Project Report | A comprehensive report that summarizes the entire project and potential for future work presented to all stakeholders. |

## Boundaries

Inclusive boundaries are:

- Data Preprocessing: handling missing values, encoding, normalization and detecting outliers

- Model development: classification and regression models will be trained using a subset of the data and validated using a test dataset. Performance metrics such as accuracy, F1-score (for classification), and Mean Squared Error (for regression) will be calculated. Model explainability tools will be used to highlight which features contribute most to the predictions

- Dashboard/Interface: to input patient data (e.g., age, symptom type) and receive predictions in real-time about the dominant OCD feature and the severity of symptoms

- Ethical considerations: data privacy and security.

Exclusive boundaries:

- The model will not diagnose OCD or other mental health disorders

- The model will not recommend treatments

- The patient cannot input data

- The model will not track data from any wearable devices

# Duration

## Timeline

| Start Date | Completion Date | Task | Duration (Days) | Dependencies |
| --- | --- | --- | --- | --- |
| 2/9 | 8/9 | Finish Project Plan and Stakeholder Requirements | 5 | None |
| 9/9 | 22/9 | Finish Project Charter | 10 | Completion of the one above |
| 13/9 | 17/9 | Data is Preprocessed | 3 | None |
| 9/9 | 30/9 | Complete First Version and Demonstrated | 15 | Completion of all above |
| 1/10 | 1/10 | Test on experts in IT and healthcare | 1 | Completion of all above |
| 30/9 | 6/10 | Adjustments Made | 5 | Completion of all above |
| 7/10 | 20/10 | Data Mining Completed | 10 | Completion of Data Preprocessing and First Version |
| 20/10 | 27/10 | Final Reporting and Project Close | 5 | Completion of all previous tasks |

## Executive Milestones

The table below lists the high-level Executive Milestones of the project and their estimated completion timeframe.

| Executive Milestones | Estimated Completion Timeframe |
| --- | --- |
| Project planned and dataset chosen | Week 1 |
| Requirements from stakeholders | Week 1 |
| Project Charter Done and Project Approved to Proceed | Week 3 |
| Data Preprocessing | Week 3 |
| Version 1 Ready and demonstrated to stakeholders. | Week 5 |
| Test on experts in IT and healthcare | Week 5 |
| Adjustments Made | Week 6 |
| Data Mining | Week 7 |
| Final Reporting and Project Close | Week 8 |

# budget Estimate

## Funding Source

The project will be financed by the following founding sources:
 
Operational Budget: The main funding source will be from the Region Stockholm operational budget allocated to research and development projects. Every year Region Stockholm funds research and innovation projects to improve healthcare (11). This will include consultant hire which in turn involves personnel costs.

Grants: Additional funding might be found from grants available for mental health research projects. 

In-kind Contributions: Contributions such as the use of personal computers will support the project and reduce direct costs.

## Estimate

This section provides a summary of estimated spending to meet the objectives of the Predicting OCD Severity: Impact of Demographic and Clinical Features project as described in this project charter.  This summary of spending is preliminary and should reflect costs for the entire investment lifecycle.  It is intended to present probable funding requirements and to assist in obtaining budgeting support.

- Personnel costs: 500 000 SEK - This  includes salaries for the whole consultant team consisting of six Health Informaticians who all work from home. The health informaticians have different roles described later in this Project Charter.

- Data Processing and Computational Resources: 50 000 SEK - the team members' own contributions will contribute to this project using less money. Some open source software licenses will be used as well as an open access dataset which also will reduce the costs. However, some licenses will be needed. SLL certificate to secure the web application, compliance tools for GDPR Auditing and Cloud Services will be needed.

- Testing on experts: 0 SEK - Compensation will be given in the trade of letting another group test their solution on us. No expenses here.

- Miscellaneous Costs: 50 000 SEK - This covers unforeseen costs such as any unexpected consultation fees or technical support, unforeseen documentation cost and unforeseen delay of project due to sick-leave.

Total Budget: 600 000 SEK

# High-Level Alternatives Analysis

- Using existing machine learning models or prediction tools that have been

applied to mental health conditions are one alternative to developing a custom prediction model for OCD symptom severity. These model can be further worked on to predict outcomes of psychiatric disorders and essentially be adapted for the OCD dataset. Many studies have been performed related to OCD prediction models in one way or the other over the years (12), however, they do not fully address the unique factors present in this dataset such as Y-BOCS scores for obsession and compulsions or allow deep customizations necessary for our dataset.

- Another alternative could be using COTS data analysis platforms, for instance; SAS analytics, Microsoft Azure Machine Learning Studio, or Google Cloud AI platform, that provide ready-made machine learning models and data visualizations for healthcare data analysis. While these models could help with quick deployment of models and dashboards, saving time on custom development, there is lack of flexibility to customize the model for specific attributes in our dataset for predicting severity of obsessive and compulsive symptoms. Additionally, other drawbacks when considering COTS products include that these may require further licensing which can be costly and offer limited integration with our dataset.

# Assumptions, Constraints And Risks

## Assumptions

This section identifies the statements believed to be true and from which a conclusion was drawn to define this project charter.

- It is assumed that the clinical and demographic data provided in the OCD patient dataset is accurate and complete. This assumption plays a vital role in this project because any inaccuracies in the data such as input errors or faulty results could lead to incorrect analysis and predictions. This project relies on the assumption that the dataset shows accurate patient population for drawing meaningful insights.

- Another assumption is that the data format such as column names, data type, etc will remain consistent with further data updates in the future to limit extra preprocessing which can delay analysis.

- Since the dataset is synthetic and created by AI, it does not contain real patient information, which reduces the risk of legal and ethical concerns related to privacy and security. However, all legal and ethical guidelines are assumed to be followed such as General Data Protection Regulation (GDPR) or Health Insurance Portability and Accountability Act (HIPAA). This ensures that patient data can be used in the future without any legal or ethical concerns.

## Constraints

This section identifies any limitation that must be taken into consideration prior to the initiation of the project.

- There are time constraints for data processing, model and dashboard deployment, given the scope of the project. The data analysis for this type of dataset may require a lot more time than 8 weeks, which can pose a challenge for completion of the project.

- Another constraint is budget, which for this project is 600,000 SEK, that covers personnel costs and other expenses. This limited budget may hinder the project if another expert need to be hired or to combat unforeseen challenges.

- Obtaining feedback from the end user is one of the vital aspect of the project to validate the product and to ensure that it meets all the requirements. However, it can be difficult to gain access to Healthcare professionals for testing.

## Risks

This section describes the risks associated with the project.

| Risk | Mitigation |
| --- | --- |
| Time Management | Develop detailed project plans and deadlines. Tasks are assigned to each member of the team equally and frequently check-ins with all members to monitor progress and address any delays. |
| Change in requirements | Clear project aim and deliverables are set from the start of the project. A change management process can be set up to manage any changes to the project requirements and their impact on time and budget. |
| Data security | Compliance with relevance regulations like HIPAA, GDPR, etc to ensure data security. Use secure methods for storing and handling data and regular reviews of security practices. |
| Company Feedback | Regular communication and check-ins with the company are scheduled to ensure that the project is on track and in line with the requirements. All feedback is documented and included in the project plan. |

# Project Organization

## Roles and Responsibilities

This section describes the key roles supporting the project.

| Name & Organization | Project Role | Project Responsibilities |
| --- | --- | --- |
| <Name> <Org> | Project Manager | Person who performs the day-to-day management of the project and has specific accountability for managing the project within the approved constraints of scope, quality, time, and cost, to deliver the specified requirements, deliverables, and customer satisfaction. This person also serves as the interface between the team and the government, ensuring clear communication, managing approvals, and providing regular updates to the governmental stakeholders. |
| <Name> <Org> | Business Lead | Person in management who is responsible for the project in its entirety. This person ensures that the project aligns with the business's strategic goals, financial performance, and compliance with governmental objectives. This person approves the request for funding, approves the project scope, and sets the priority of the project relative to other projects in the business. |
| <Name> <Org> | Technical Lead | The Technical Lead is a data scientist who is responsible for providing technical direction to the project. Including the details of system development and overseeing the machine learning model development. Will work closely with the Clinical Lead to ensure that the model aligns with clinical realities and standards of care for OCD. |
| <Name> <Org> | Security Lead | Person who is responsible for maintaining the project’s information security. The security steward also ensures the security of patient data and that the project follows GDPR. |
| <Name> <Org> | Clinical Lead | The Clinical Lead can be a psychologist or mental health expert who ensures that the patterns identified by the machine learning model reflect clinically meaningful insights into OCD. They will also validate the model’s output and provide domain expertise during development. |
| <Name> <Org> | Quality Lead | The Quality Lead ensures that both technical functionality and clinical accuracy are met and assess the model’s clinical relevance alongside system performance. This includes developing and executing testing plans, assessing model accuracy, usability, and security compliance, and overseeing the reliability of the system across different scenarios. |

## Stakeholders (Internal and External)

| Name | Description |
| --- | --- |
| Internal |  |
| Data Science Team | Responsible for developing and refining the predictive model based on the dataset of OCD patients. |
| Clinical Team | Their input will be critical in ensuring the clinical validity of the patterns identified and verifying the usefulness of the model in real-world scenarios. |
| Project Management | Oversees the execution of the project to ensure it stays on budget and schedule while meeting its objectives. |
| External |  |
| Patients | The beneficiaries of the project. The insights gained from predicting OCD symptom severity can help personalize treatment plans and improve patient outcomes. |
| Healthcare Providers | Providers delivering patient care who may utilize the predictive model to improve diagnosis and treatment approaches for OCD. |
| Mental Health Researchers | Those conducting further studies on OCD and related disorders may use the model to understand the factors contributing to OCD symptom severity. |
| Governmental Health Agencies | Regulatory bodies in the region of Stockholm that oversee mental health standards and may use the findings to inform public health policies and treatment guidelines for OCD. |
| Technology partners | Vendors or developers who provide the infrastructure, software, and tools necessary to support the development, integration, and deployment of the predictive model. They ensure the model operates efficiently within existing systems, enabling data analysis, storage, and secure access for stakeholders |
| Insurance Companies | May use the insights from the model to adjust coverage policies regarding health insurance based on predicted treatment outcomes for OCD patients. |

## Development approach

The waterfall development methodology has been selected for the OCD severity prediction model due to its structured and linear approach, which aligns well with the defined stages of the model development [13]. This method also ensures that each phase—requirements gathering, data preparation, model development, testing, and refinement—progresses in a linear and controlled manner [13]. Since the project is using a synthetic dataset in this pilot phase, the requirements gathering and analysis phases can be completed upfront; which is a key strength of the waterfall approach. Additionally, the emphasis on comprehensive planning and design before model implementation can further help mitigate potential risks, such as managing sensitive medical data, ensuring data security, and effective time management, as outlined in point 8:3 [13]. 
So far, the project has been progressing smoothly through the initial phases. The requirements gathering phase has been completed, focusing on key tasks such as initiating the project, establishing milestones and goals, and delegating roles. The team has now moved into the design phase, where we are creating detailed specifications for the prediction model. Subsequent phases will include implementation, where the team will focus on developing and refining the model; testing, which will involve validating clinical outcomes; and maintenance, during which stakeholder feedback will be collected to ensure the model's relevance and practical applicability.

# project Charter approval

The undersigned acknowledge they have reviewed the project charter and authorize and fund the "Predicting OCD Severity: Impact of Demographic and Clinical Features" project.  Changes to this project charter will be coordinated with and approved by the undersigned or their designated representatives.

| Signature: |  | Date: | 19/09/24 |
| --- | --- | --- | --- |
| Print Name: | Mathilda Wendt |  |  |
| Title: | Project Manager |  |  |
| Role: | Oversees project execution |  |  |

| Signature: |  | Date: | 19/09/24 |
| --- | --- | --- | --- |
| Print Name: | Shweta Ghaisas |  |  |
| Title: | Technical Lead |  |  |
| Role: | Oversees Technical development |  |  |

| Signature: |  | Date: | 19/09/24 |
| --- | --- | --- | --- |
| Print Name: | Ye Htut |  |  |
| Title: | Technical Lead |  |  |
| Role: | Oversees Technical Development |  |  |

| Signature: |  | Date: | 19/09/24 |
| --- | --- | --- | --- |
| Print Name: | Amanda Bashiri |  |  |
| Title: | Quality Lead |  |  |
| Role: | Ensures technical functionality and clinical accuracy |  |  |

| Signature: |  | Date: | 19/09/24 |
| --- | --- | --- | --- |
| Print Name: | Sidra Jahanzeb |  |  |
| Title: | Business Lead |  |  |
| Role: | Oversees Overall business requirements of the whole project. |  |  |

| Signature: |  | Date: | 19/09/24 |
| --- | --- | --- | --- |
| Print Name: | Moa Osterberg |  |  |
| Title: | Business Lead |  |  |
| Role: | Oversees Overall business requirements of the whole project. |  |  |

APPENDIX A: DOCUMENTATION

The following image shows the Jira board through which the project manager assigns tasks

APPENDIX B: REFERENCES

- Stein DJ, Costa DLC, Lochner C, Miguel EC, Reddy YCJ, Shavitt RG, van den Heuvel OA, Simpson HB. Obsessive-compulsive disorder. Nat Rev Dis Primers. 2019 Aug 1;5(1):52. doi: 10.1038/s41572-019-0102-3.

- Carney TJ, Wiltz JL, Davis K, Briss PA, Hacker K. Advancing Chronic Disease Practice Through the CDC Data Modernization Initiative. Prev Chronic Dis. 2023 Nov 30;20:E110. doi: 10.5888/pcd20.230120. PMID: 38033272; PMCID: PMC10723079.

- CDC. Advancing Science and Health Equity [Internet]. US: CDC; 2024. [cited 2024 Sep 9]. Available from: https://www.cdc.gov/about/priorities/index.html

- US Department of Health and Human Services(DHHS). Strategic Goal 3: Strengthen Social Well-being, Equity, and Economic Resilience[Internet]. US: DHHS; [date unknown]. [updated 2024 Jan 23, cited 2024 Sep 9]. Available from: https://www.hhs.gov/about/strategic-plan/2022-2026/goal-3/index.html

- US Department of Health and Human Services(DHHS). Strategic Goal 4: Restore Trust and Accelerate Advancements in Science and Research for All [Internet]. US: DHHS; [date unknown]. [updated 2024 Jan 19, cited 2024 Sep 9]. Available from:  https://www.hhs.gov/about/strategic-plan/2022-2026/goal-4/index.html

- HealthIT.gov, 2020-2025 Federal Health IT Strategic Plan. US: DHHS IT; 2020. [cited 2024 Sep 9]. Available from: https://www.healthit.gov/topic/2020-2025-federal-health-it-strategic-plan

- President’s Management Agenda (PMA). Delivering Excellent, Equitable, and Secure Federal Services and Customer Experience [Internet]. US: PMA; [date unknown]. [cited 2024 Sep 9].   Available from: https://www.performance.gov/pma/cx/

- President’s Management Agenda (PMA). Managing the Business of Government [Internet]. US: PMA; [date unknown]. [cited 2024 Sep 9].   Available from: https://www.performance.gov/pma/businessofgov/

- Karolinska Institutet(KI). Strategy 2030 - Creating Karolinska Institutet's future together. Stockholm, Sweden: KI; 2019. [cited 2024 Sep 14]. Available from: https://ki.se/en/about-ki/strategy-and-core-values

- Folkhalsomyndigheten. National public health goal and target areas [Internet]. Sweden: Folkhalsomyndigheten; [date unknown]. [updated 2024 May 24, cited 2024 Sep 14]. Available from: https://www.folkhalsomyndigheten.se/om-folkhalsa-och-folkhalsoarbete/tema-folkhalsa/vad-styr-folkhalsopolitiken/nationella-mal-och-malomraden/

- Region Stockholm. Forskning och innovation [Internet]. Stockholm: Region Stockholm; 2023 [cited 2024 Sep 12]. Available from: https://www.regionstockholm.se/forskning-innovation/

- Szalisznyó K, Silverstein DN. Computational Predictions for OCD Pathophysiology and Treatment: A Review. Front Psychiatry. 2021 Oct 1;12:687062. doi: 10.3389/fpsyt.2021.687062.

- Atlassian. Waterfall Methodology for Project Management [Internet]. Atlassian. 2023. Available from: https://www.atlassian.com/agile/project-management/waterfall-methodology